## Action Plan
Action Plan
| Action | Deliverables*/Activities | Send Deliverable To: | Tools | Data Collection Resources in Cabinet | Who Will Complete? | # of people | Estimated Time to Complete | Start Date | Due Date | Done?
1 | Develop Agency Data Collection Plan | None | N/A | Guidebook 1, Action Plan.xls | Department Heads/Mgrs., Personnel Administrator | Organization/Workforce Team | Depends | 1 day |  | Now
2 | Consult with Agency Leaders | Memo to Request Meeting | Cabinet Sec. or Constitutional Officer | Talking Points in Guidebook, Memo to Leadership.doc |  | AIL (or designee, if several per Cabinet) | 1 to 2 | ½-1 hour |  | 1998-09-04
|  | Meeting with Leadership | Cabinet Sec. or Constitutional Officer | Talking Points in Guidebook |  | AIL (or designee, if several per Cabinet) | 1 to 2 | 1-2 weeks |  | 1998-09-04
3 | Inform Data Resources and A. S. Employees | Memo to Data Collection Resources | Department Heads and Mgmt | Memo to Data Resources.doc, Memo to A.S. Employees.doc, Talking Points in Guidebook |  | AIL (or designee, if several per Cabinet) | 1 to 2 | ½-1 hour |  | 1998-09-04
4 | Complete Org_Template | Org_Template.xls (1 file per agency) | Gail Prewitt | Guidebook 1, Org_Template.xls, Module 1.3 | Organizational Chart, Personnel Administrator, Dept Heads/Mgmt | Implementation Team designee | 1 to 3 | 1-4 days |  | 1998-09-14
5 | Complete Personnel Data Worksheet | ###_Data.xls (1 file per department, ### = agency/dept name) | Gail Prewitt | Guidebook 1, Activities Dictionary, Dept_Data.xls, Modules 1.3 & 1.4 | Personnel Administrator, Dept Heads/Mgmt, as needed | Personnel Administrator | 1 | 1-7 days |  | 1998-09-14
6 | Complete Activities Worksheets | ###_Data.xls (1 file per department, ### = agency/dept name) | Gail Prewitt | Guidebook 1, Dept_Data.xls, Personnel Data Worksheet, Module 1.3 | Department Heads/Mgrs., Personnel Administrator, Recent Evaluations (only if needed) | Implementation Team designee | Depends on Complexity of Agency | 3-4 weeks |  | 1998-10-15
7 | Complete Training_Worksheet | ###_Data.xls (1 file per department, ### = agency/dept name) | Gail Prewitt | Guidebook 1, Training Worksheet, Personnel Data Worksheet, Module 1.4 | Personnel Administrator, GSC Liaison | GSC Liaison (Registrar Teaching System) | 1 | 1-2 days |  | 1998-10-15
8 | Submit current position description forms. | ###.doc, 1 per employee. Submit on disk or print out. (### = Social Security #) | Gail Prewitt | Guidebook 1, PD Form.doc, Module 1.4, Activities Worksheets | Personnel Administrator, Dept. Heads/Managers | Personnel Administrator Managers | Depends | 1-4 weeks |  | 1998-11-30
* Deliverables can be turned in either by disk or e-mail
Note on B3: List the steps in the data collection process.
Note on C3: List the deliverable that is due with each step.
Note on D3: Indicate who should receive the deliverable.
Note on E3: List the tools that are available to help you complete this step.
Note on F3: List the resources who can provide this data.
Note on G3: Indicate which member of the Implementation Team will complete this task.
Note on H3: This shows the number of individuals who may be required to collect the data and complete each deliverable.
Note on I3: This column shows the approximate time that will be required to complete each task.
Note on J3: Fill in the date that this step should be started.
Note on K3: These are the due dates for each deliverable.
Note on L3: This column provides a checklist where you can indicate when the task is completed.