Course 2: Administrative Services Workforce Transition Preparation for Agencies

Guidebook – Course 2

Table of Contents

Introduction	3

Helpful Definitions	4

The Workforce Transition Development Process and Tools	5

Step 1: Develop a Transition Plan	6

Purpose	6

Resources Needed	6

Tools and Examples	6

Procedure	6

Step 2: Review As-Is Data	9

Purpose	9

Resources Needed	9

Tools and Examples	9

Procedure	9

Step 3: Complete Roles Sheet	11

Purpose	11

Resources Needed	11

Tools and Examples	11

Procedure	12

Step 4: Complete Training Sheet	16

Purpose	16

Resources Needed	16

Tools and Examples	16

Procedure	16

Step 5:  Identify Potential Consolidation Areas	19

Purpose:	19

Resources Needed	19

Tools and Examples	19

Procedure:	19

Step 6:  Complete Redeploy Sheet	26

Purpose	26

Resources Needed	26

Tools and Examples	26

Procedure	26

# Introduction

This Guidebook contains instructions on how to develop a workforce transition plan for your agency’s administrative services functions.  The purpose of the guidebook is to minimize the amount of data you will need to enter by using information that you have already provided through the as-is activity data collection process.

The tools and processes described will help your agency:

- Ensure that all administrative services management and their employees understand their future roles and tasks;

- Identify who needs what types of training when;

- Identify security profiles for employees to ensure that they have appropriate access to documents and approvals; and

- Prepare for redeploying employees as necessary.

The process involves six primary steps.  To facilitate this process and ensure that all agencies use a consistent, systematic and objective approach to MARS implementation, you have been given a series of Microsoft Word and Microsoft Excel tools.  This Guidebook provides step-by-step instructions to completing these tools and other data collection activities.

# Helpful Definitions

Before beginning the planning process, it may be helpful for you to review some definitions specific to the Simplified Administrative Services Project.  The following resources may be helpful to you in this regard:

Guidebook 1: Definitions

The Guidebook supplied during Course 1 provides an overview of terms and concepts associated with the Simplified Administrative Services Project.  Located in your Course 1 materials, it appears under the tab, "Guidebook 1: Definitions."  It may be helpful for you to review -- and perhaps share with colleagues -- as you are working through the following steps.

MARS Page of the Simplified Administrative Services Web Site

For those still becoming familiar with MARS terminology, the MARS page of the Simplified Administrative Services Web Site is a great place to visit.  It is located at the following site:

http://www.state.ky.us/agencies/adm/mars/mars.htm

On this page, you will find a wealth of information, including:

- Presentations made at previous training sessions on topics such as "What is MARS," "MARS Chart of Accounts Overview," and the "MARS Training Kickoff."

- An overview section for each of the Administrative Services teams that supplies information about project background, goals and benefits, and a view to the organizations affected.

- A "Frequently Asked Questions (FAQ)" section for MARS, Business Improvement and Change Leadership questions.  To make it easier for you to find the information you need about MARS, those questions and their respective responses are sorted into the categories of Technical (specific to the MARS software application), Functional (dealing with how MARS will affect the Commonwealth's business practices), and Other.

- The MARS page has search functionality that allows you to enter a word or phrase about which you'd like information.  If such information is contained on the page, it will be found for you automatically.  If you don't find what you need, consider submitting a question via FAQ.

The Administrative Services page is continually updated, so visiting it frequently will help to ensure that you have the most up-to-date information available.  New information is flagged with the word "Updated" to help you spot what's new.

# The Workforce Transition Development Process and Tools

Preparing for an effective workforce transition involves understanding the future roles of your agency’s employees and creating a plan that will address each employee’s needs at the right time, with the right information.

The following illustration provides an overview of the six major steps in the development process.  You may not need to complete all of these steps if your agency is small or limited in administrative services functions.

Review

As-Is Data

Data

Complete Roles Sheet

Ro

R

As

s

shee

Complete

Training

Sheet

Identify

Consolidation

Areas

Complete

Redeploy

Sheet

Develop Transition Plan

A Diskette was provided to your team during training.  As shown in the table below, this diskette contains workforce transition tools and role information.  All of the files are either Microsoft Word, PowerPoint, or Microsoft Excel files that have been saved in formats compatible with Microsoft Office 95 or later.

Disk contains:

Roles (Folder) Roles.zip

Tools (Folder)

WT_ PLAN.doc

exercise.zip

AsIs_ToBe.ppt Guidebook2.zip

The tools have been designed with on-line instructions to make data entry as convenient as possible.  The following pages provide more detailed instructions and background information to help you understand the process.

## Step 1: Develop a Transition Plan

Purpose

SAMPLE:

Memo to AS Employees.doc

A plan will help you organize your agency's workforce transition efforts and present your agency's philosophy for the transition. Plans provide a way to track what needs to be done, who needs to do it, corresponding deadlines, and status.  The plan should make it easier for you to manage the multiple tasks and responsibilities your agency faces.  The sample and guidelines provided to you are intended as a starting point to launch your agency's efforts.

### Resources Needed

Following the training, meet with the appropriate designated Agency Implementation Team members to establish a Plan.  A Transition Planning template has been provided in your handouts.  An electronic copy of this document, WT_Plan.doc, is saved on the Disk in the Tools folder.

### Tools and Examples

This document, entitled "GUIDE TO DEVELOP AGENCY WORKFORCE TRANSITION PLAN," lists key steps your agency should consider for workforce transition.  It then details for each step a description of the action items and provides space to capture for each item the date needed, person assigned to, and status.  There is also a Workforce Transition Plan sample that was used by Administrative Services for warehouse optimization efforts.

### Procedure

The procedures for using this template were briefly described during training in Module 2.4.  Those procedures have been recapped below, for your future reference.  The first page of the template also appears in this section, for your reference.  Please use the template and the following steps as a guide to develop your plan.

- Open "WT_Plan" found on the Course 2 diskette.

- Determine whether additional Action Items will be required for your agency.

- If so, insert rows into the table to allow for these Action Items to be added.  Fill out the "Action Item" column(s) for added items.

- Complete the "Description/How To" and the "Date Needed/Timeframe" columns for any new Action Items added.

- For added as well as existing Action Items, allocate resources and record names in the "Assigned To:" column.  Focus on assigning resources for tasks due sooner.  For tasks having a longer-term timeframe, resource assignments may be made at a later date.

- Once you finish a draft of a Workforce Transition Plan for your agency, be sure to save the file!

- Establish a schedule by which the "status" column will be updated.  For example, you might decide to have weekly or bi-weekly meetings with each of the resources involved.  After each such meeting or communication, it is recommended that you update your plan.  It is also suggested that you make plan updates available to the resources involved, so that they may also use them to guide their activities.

- Monitor progress made toward each item on your plan, ensuring that needed items are completed.

Guide to Develop Agency Workforce Transition Plan

Guide to Develop Agency Workforce Transition Plan

## Step 2: Review As-Is Data

Purpose

SAMPLE:

Memo to AS Employees.doc

The purpose of reviewing the As-Is Information is to make sure it is accurate before completing the other worksheets in the [Agency#]_[DeptName]_ WkfrTran. XLS file.  The other worksheets use the as-is data as a starting point to help you determine the to-be roles and training needs for your employees.

### Resources Needed

To review the “As-Is Information” worksheet in the [Agency#]_[DeptName]_ WkfrTran. XLS file, you may need to consult:

- Copies of the original as-is data that you submitted

- As-Is Activities Dictionary

- Changes in staffing since you submitted your agency's data

### Tools and Examples

[Agency#]_[DeptName]_ WkfrTran. XLS] is a Microsoft Excel file you received via e-mail.  The “As-Is Information” worksheet is the first worksheet in this Excel file.  An example of this worksheet is included at the top of page 9.  For additional examples, please refer to the Module 2.4 slides that were provided during training.  If you require assistance with Microsoft Excel, please consult Appendix E: Software Assistance Guide from Guidebook 1 provided at Course 1 in August and September 1998.

### Procedure

The procedures for completing this template were briefly described during training Module 2.4.  Those abbreviated procedures have been broken into a number of more detailed steps for you here.

- Open the Microsoft Excel file, [Agency#]_[DeptName]_ WkfrTran. XLS], located on the Course 2 diskette.

- Select the worksheet entitled, “As-Is Information.”

- When you open this worksheet, you will see five column headings, entitled:

- Name (last, first)

- Personnel Information

- Financial Mgt Total

- Material Mgt Total

- Other Total

Sample “As-Is Information” Worksheet

These columns contain the information that your agency submitted during the as-is activity data collection process.  Review the list of employee names that is provided.  If you would like to add someone to this list who participates in administrative services activities in your agency, include their name at the bottom of the list, and fill out the other columns on this worksheet as needed.

- To validate or change an employee’s as-is personnel information, click on the “+” sign above the Personnel Information column.  This will unhide columns containing the specific information your agency submitted during the as-is activity data collection process.  Clicking on the “-“ sign above the Personnel Information column will hide the other columns again.

- To view the as-is activities that make up the total of financial management, material management, or other activities, click on the “+” sign above each of these columns.  Keep in mind that these totals are unlikely to be an exact measure of the amount of time an employee spends on administrative activities.  It is expected, however, that these totals are a good approximation of how much time an employee spends on administrative activities.

- If you know of any changes that have been made to the time spent by individuals in these areas, update the spreadsheet to reflect them.

- If you have no changes to make to this information, you are ready to proceed.

## Step 3: Complete Roles Sheet

### Purpose

The purpose of completing the roles sheet is to identify the “to-be” roles for each employee in your agency who performs administrative services functions.  The “to-be” role identification is the basis for understanding how individual employees will be affected by the MARS implementation.  In addition, completing this worksheet allows you to identify employees who may be eligible for redeployment or transition.

### Resources Needed

To complete the “To-Be Roles” worksheet in the [Agency#]_[DeptName]_ WkfrTran. XLS] file, you may need to consult:

- The “As-Is Information” worksheet

- The handout from Module 2.4 training that maps As-Is Activities to To-Be Roles.  Also located on disk 1 as As Is-To Be.ppt

- The handout which lists all of the To-Be Roles that have been identified

- The Curriculum Handbook

### Tools and Examples

[Agency#]_[DeptName]_ WkfrTran. XLS] is a Microsoft Excel file located in the Tools file folder on the Course 2 diskette provided with the Guidebook.  The “To-Be Roles” worksheet is the second worksheet in this Excel file.  An example of this worksheet is included below.  For additional examples, please refer to the Module 2.4 slides that were given to you during training.

Sample “To-Be Roles” Worksheet

### Procedure

The procedures for completing this template were briefly described during training Module 2.4.  Those abbreviated procedures have been broken into a number of more detailed steps for you here.

- Open the worksheet entitled, “To-Be Roles”.  You will see your list of employee names in the first column.  These names are automatically filled in based on the information in the “As-Is Information” worksheet.

- The next column asks whether an employee will use MARS.  Fill in this information for each employee on the list by clicking on the cell next to the employee’s name.  A drop down menu will appear, allowing you to select either “yes” or “no”.

- For each employee that will be using MARS, use the next column to fill in the date when the individual will begin using MARS.  Please enter both the month and year.  For example, July 1999 would be entered as 07/99.

- The next column asks whether this individual will have an administrative services role in the future.  Fill in this information for all of the employees on your list.  To do this, click on the cell and select “yes,” “no,” or “maybe” from the drop down menu.

- The next steps allow you to identify the “to-be” roles for the individuals in your agency who will be performing administrative services roles in the future.  Begin this process by clicking on the “+” sign above the role identification column.  This will unhide columns entitled “Role 1” through “Role 10.”  If an individual will NOT be performing administrative services in the future, this section should not be completed.

- To select a to-be role for an employee, click on a cell under the “Role 1” column.  A list of roles will appear as a drop down menu.  (For your convenience, this list of roles can be found on the next page and is a separate tab in the Excel file).  Select a role from this list.

Note:  The handout from training Module 2.4 that maps the “As-Is Activities” to the “To-Be Roles” will also assist you in selecting the to-be roles for an employee.

“To-Be” Roles List:

| Prepare and Manage Detailed Agency Budgets | Establish Agency Workflow |
| --- | --- |
| Manage Budget Appropriations and Allotments | Records Management |
| Biennial Budget Preparation | Agency System Administration |
| Generate Disbursements |  |
| Request Immediate Check from Treasury |  |
| Establish Payable (Straight Disbursement) |  |
| Establish Recurring Payable |  |
| Monitoring and Approval of Disbursements and Payables |  |
| Administer Procard |  |
| Consumable Inventory Management |  |
| Fixed Asset Property and Insurance Control Management |  |
| Supervision of Fixed Asset Property |  |
| Asset/Liability Management |  |
| Monitoring Payables |  |
| Agency Fiscal Management/ Supervision |  |
| Table Maintenance |  |
| Error Correction |  |
| Maintain Codes |  |
| Processing Journal Vouchers |  |
| Processing/ Manage Loans |  |
| Manage Funds Availability |  |
| Accounting Manager |  |
| Grant Setup, Monitoring & Reporting |  |
| Grant Management |  |
| Cost Allocation Expert |  |
| Process Internal Bills - Buyer |  |
| Process Internal Bills - Seller |  |
| Goods and Services Procurement |  |
| Initiate and Request Goods or Services |  |
| Purchasing Support |  |
| Receiver |  |
| Contract Administration |  |
| Create & Process Accounts Receivable |  |
| Approve Accounts Receivable |  |
| Initiate Cash Receipts |  |
| Cash Receipts Support |  |
| Create and Process Cash Receipts |  |
| Internal Approval of Cash Receipts |  |
| Final Approval of Cash Receipts |  |
| Maintain Customer Files |  |
| Collection of Delinquent Accounts Receivables |  |
| Write-Off Delinquent Accounts Receivable |  |
| Prepare Expense Voucher |  |
| Authorize Expense Voucher |  |
| Financial Reporting |  |
| Agency Security Management |  |

- You may select up to 10 “to-be” roles for an employee.  As we discussed in the training, an individual may have several roles, or may perform only one role.  To select additional roles for an employee, enter the roles under the columns headed “Role 2”, “Role 3,” etc.  It does not matter in what order you enter the roles for an employee.

- For each role, you may enter an effective date and comments.   To enter this information, click on the “+” sign which is located above the “Role” column.

- After you have finished entering all of the role information for each employee, click on the “-“ sign above the “Role Identification” column.  This will hide the “Role” columns from view.

- The next column asks whether an employee may require redeployment.  To complete this information, click on the cell and a drop down menu appears allowing you to select “yes,” “no,” or “maybe.”

Note: This column will probably not be applicable until December 1999 and beyond.  You may want to leave it blank right now.

Any employee whose job activities will be reduced by 25% or greater should receive a maybe.  Any employee whose job activities will be reduced by 75% or more should receive a yes.

- For employees who may require redeployment, you may enter the anticipated transition date in the next column.  Please enter this information as a month and year (i.e. 07/99).

- To further assist with your workforce transition planning, the next column asks whether an employee may retire in the next 3 years.  To complete this information, click on the cell and a drop down menu appears allowing you to select either “yes” or “no.”

- For employees who may retire in the next three years, the last column asks you to enter the anticipated retirement date.  Again, please enter this information as a month and year (i.e. 07/99).

- Once you have completed this spreadsheet (see below for an example of a completed spreadsheet), save the file!  You are then ready to proceed.

Sample Completed “To-Be Roles” Worksheet

## Step 4: Complete Training Sheet

### Purpose

The purpose of completing the training sheet is to identify the courses that employees in your agency will need to work effectively after MARS is implemented.

### Resources Needed

In order to complete the “Training” worksheet in the [Agency#]_[DeptName]_ WkfrTran. XLS] file, you may need to consult:

- The “To-Be Roles” Worksheet

- The Role Templates

- The Curriculum Handbook

### Tools and Examples

[Agency#]_[DeptName]_ WkfrTran. XLS] is a Microsoft Excel file located in the Tools file folder on the Course 2 diskette provided with the Guidebook.  The “Training” worksheet is the third worksheet in this Excel file.  An example of this worksheet is included below.  For additional examples, please refer to the Module 2.4 slides that were given to you during training.

### Procedure

The procedures for completing this template were briefly described during training Module 2.4.  Those abbreviated procedures have been broken into a number of more detailed steps for you here.

- Open the worksheet entitled, “Training.”  A sample of this worksheet is included at the top of the next page.  The first column contains a list of employee names that have been filled in automatically based on your “as-is” information.

- The next column asks whether an individual will require MARS training prior to 7/1/99.  Enter “yes” in this column if the employee will be using MARS as of July 1, 1999.

- If an individual will not require MARS training prior to July 1, 1999, but will require MARS training in the eighteen months after MARS is implemented, enter “yes” in Column C.  Column D allows you to enter the month/ year that the first training would be expected to be needed after July 1999.

Sample “Training” Worksheet:

- The “Course Identification” column allows you to enter the specific MARS training courses that an individual may require.  To enter courses, click on the “+” sign above the “Course Identification” column.

- Click on a cell and a drop down menu appears listing the MARS training courses that are available.  You may select up to 10 courses for an individual.  Clicking on the “+” sign above the course name allows you to enter an effective date for the course (date course is actually scheduled) as well as additional comments (e.g. date by which you need the course, contingencies, etc.).  A complete list of the MARS training courses is also listed below for your reference:

Course List:

| Chart of Accounts | Payables |
| --- | --- |
| Budget and Cash Control | Contracting |
| General Accounting | Procurement Card Administration |
| External Vendor Payment Processing, Internal Payments, and Automated Disbursements | PD-Web PD System Administration Budget Preparation |
| Revenue and Receivables |  |
| Consumable Inventory | Budget Execution |
| Fixed Assets | BRASS - System Administration |
| Projects and Grants | Crystal Information |
| Advanced Projects and Grants | Reports |
| Control Agency |  |
| Cost Allocation |  |
| Travel |  |
| General Procurement |  |

- The final column allows you to enter additional training needs that an employee may require, such as the Statewide budget process, customer service, or accounting.

## Step 5:  Identify Potential Consolidation Areas

### Purpose:

Understanding where efficiencies are anticipated and which activities will go away will provide you with the information you need to make decisions regarding your agency's workforce transition.  The following steps aim to help you identify these critical activities, and couple this information with agency-specific data.

### Resources Needed

- As-Is data from fall submission (if you do not have it electronically, contact Gail Prewitt via e-mail or phone 502-564-4240)

- Current agency-specific staff information

- Activity_Consolidation.xls

- Data from agency administrative services management about MARS impact and efficiencies

- Workforce Transition Tracking Tool ([Agency#]_[DeptName].xls)

### Tools and Examples

[Activity_Consolidation] is a Microsoft Excel file that will be sent to you via Outlook e-mail.  This file contains 2 worksheets, "Activities_No Longer" for those activities that will not need to be performed in the MARS environment and ""Activities_Efficiencies" for those expected to be done more efficiently within MARS operations.

### Procedure:

1.0 	Verify existing "as-is" information for your agency

Resource(s):  Agency-specific "as is" personnel data collected last fall following Course 1.  Also helpful would be current agency-specific personnel data, such as an updated employee list.

1.1	Open as-is spreadsheet for agency or department.  This is the spreadsheet that you provided to us in September or October of 1998.

1.2	If you have not gone through the validation of the data and the employees, do so before proceeding to step 2.

1.3	Your validation activities should start by ensuring that each of the individuals listed on the "Personnel Data" worksheet remains with the division and branch cited, and that their respective class code and title are current.

1.4	Next, if you know of any significant changes to an individual's activities in the areas of Financial Management, Material Management, or Other Activities, record these changes on the corresponding spreadsheets.

  - Identify activities that will go away

Resource(s):  "Activities_No Longer" worksheet.  This worksheet appears at the end of this section for your use.  It will also be sent to you (within the Excel document "Activities_Consolidation") electronically via Outlook mail in the near future.

Note: the "Activities_No Longer" list is not considered exhaustive.  It is limited to those activities included on the Administrative Services Activities Dictionary that are expected to go away.  Several agencies will have additional activities that will go away once MARS implementation is completed within their organization.  You should add these activities to your master list for final calculations.

  - Calculate the total amount of time (in FTE’s) spent by your agency for each activity that will go away by creating a “Total” row after the last employee’s name on the spreadsheet.  You may want to hide the columns of the other activities to make it easier to view.  An example appears below for a fictitious agency.  You will notice that all of the activities under "Imprest Cash" are revealed, as activities in this area are expected to go away (or be significantly diminished).

  - If you would like to generate totals for specific divisions or branches in your agency, you could sort the data in the spreadsheet.  Then insert rows at the end of each sorted group to enable you to add "total" columns, as needed.

  - Create a summary list of activities that will go away and the amount of time spent by activity for your agency.  Create a total row at the bottom.  One way you can do this is by using Excel reporting functionality.

Sample Agency "As-Is" Data; Activities No Longer Performed

  - By activity, create a list of employees, amount of time spent, and the employee's location by dept and city.  Again, one way you can do this is by using Excel reporting functionality or by hiding columns and roles so that only the information you want is revealed.

- Identify target activities for efficiencies

Resource(s): "Activities_Efficiencies" worksheet.  This worksheet is also part of the "Activity Consolidation" file that you will receive electronically via Outlook mail.  This worksheet is currently being finalized.

Note: Efficiencies have been identified through conversations with the MARS Lead Subject Matter Experts (LSME's) as well as other leadership members of the Central MARS team.  As with the "Activities_No Longer" worksheet, the "Activities_Efficiencies" list is not exhaustive.  Due to individual agency circumstances and business practices, MARS may bring about even more significant efficiencies that currently expected.

  - Calculate the total amount of time (in FTE’s) spent by your agency for each target efficiency activity by creating a total after the last employee’s name on the spreadsheet.  Use the process described in step 2.1.

  - If you would like the data to be sorted in a particular way (i.e. to create totals specific to divisions or branches) refer to the suggestions in step 2.2.

  - Create a summary list of target efficiency activities with amount of time spent (in FTE's).  Again, one way you can do this is by using Excel reporting functionality or by hiding columns.

  - For each activity, create a list of employees, amount of time spent on the activity (in FTE's), and location of employee.  Again, one way you can do this is by using Excel reporting functionality or by hiding columns.

  - Calculate the amount of time your agency is targeting to be saved within an efficiency activity for your agency once MARS is fully implemented.  This number (an efficiency measure) should be expressed in the form of a percentage (e.g. .20).  Each area should have a reduction number.  You can insert a row immediately below the activity row and put the number there.

  - Calculate the difference of pre-MARS and post-MARS time spent for each target activity by multiplying the percentage of time saved by the total number of FTE's in the activity area.

An example for a fictitious agency appears below.  Note the "Efficiency Targets" row that has been inserted.  Certain agency activities corresponding to the item "Payments (Central Issued Checks)" in the Activities Dictionary have been used as an example.  Significant gains are expected in this area, due to the streamlining of existing processes via new, electronic workflow and more extensive system functionality.

Sample Agency "As-Is" Data; Target Efficiency Areas

  - This sample spreadsheet shows a subset of divisions and branches for a hypothetical agency.  Specifically, it shows the degree to which ten staff persons currently engage in activities related to "Payments (Central Issued Checks").

  - As you will notice, the efficiency targets across the activities involved vary.  It is expected that the same will be true in your agency; some activities will yield higher efficiency measures than others.

  - What is important to note in this example is that, prior to calculating efficiencies, total FTE's were found to be 4.23.  Following the introduction of efficiency measures, the total efficiency FTE's were calculated at 3.23.  What this efficiency savings of 1.00 represents is the possible extent to which FTE's may be reduced in the future.

  - Complete such calculations for all activities handled by your agency for which efficiencies are targeted.  Create a list of the changes (both positive and negative) by target activity area in FTE's.  Excel report functionality may be used to do so.

  - For target activities with significant efficiencies, identify relevant employees and positions.

  - Identify positions, as appropriate, as targets for redeployment and identify relevant timing considerations.  Use the role worksheet in the Excel tool [Agencynumber]_[DeptName]-WkfcTran.xls].

  - Reclassify or reassign duties to those who will remain in their current positions.

## Step 6:  Complete Redeploy Sheet

### Purpose

The purpose of completing the redeploy/transition sheet is to assist you with planning for workforce transition and redeployment that may be required as a result of the MARS implementation, and provide agency management with a tracking tool for helping track progress toward meeting the business case objectives.

### Resources Needed

In order to complete the “Redeploy/Transition” worksheet in the [Agency#]_[DeptName]_ WkfrTran. XLS] file, you may need to consult:

- Consolidation calculations

- As-Is Information

- Agency administrative services managers

### Tools and Examples

[Agency#]_[DeptName]_ WkfrTran. XLS] is a Microsoft Excel file located in the Tools file folder on the Course 2 diskette provided with the Guidebook.  The “Redeploy/Transition” worksheet is the fourth worksheet in this Excel file.  An example of this worksheet is included below.  For additional examples, please refer to the Module 2.3 slides that were given to you during training.  If you require assistance with Microsoft Excel, please consult Appendix E: Software Assistance Guide.

### Procedure

The procedures for completing this template were briefly described during training Module 2.4.  Those abbreviated procedures have been broken into a number of more detailed steps for you here.

- Open the worksheet entitled, "Redeploy/Transition."  A sample of this worksheet is included on the next page.  The first column is filled with the names of employees based on the "As Is Information" worksheet.  The second and third columns indicate whether an employee will require redeployment, and the anticipated transition date.  These columns are populated with the information that you supplied in columns AJ and AK of the "To Be Roles" sheet.

- The next column provides detailed information about the employee’s current class title, code, salary, and grade.  To view this information, click the “+” sign above the “Position Information” column.

- The “Special Needs” column allows you to list any special placement needs that should be considered for an employee who requires redeployment.  Examples include wheel chair, etc.

- Fill out the next three columns for employees who may require redeployment.  First, enter the beginning date of the employee’s service.  A comment box appears asking you to enter the date in the format “month/ day/ year.”  Next, enter the date that the employee was informed of the redeployment need.  Finally, enter the date of the meeting with the Personnel Cabinet or Workforce Transition Team member.

- The “New Position Tracking” column allows you to enter information related to a new position target or opportunity for an employee, including class title, class code, grade, interview date, results/ comments, and the start date for the new position.  To enter this information, click on the “+” sign above the “New Position Tracking" column.

- Finally, the last column allows you to enter the date that the employee was placed in the new position.  An example of a completed “Redeploy/Transition” worksheet is included below:

Sample “Redeploy/ Transition” Worksheet:

“